## Task List
ID | Phase | Task | Assigned Team | Team Topologies Type | Interaction Mode ("Team Topologies") | Predecessor IDs | Step Type (Lean) | Waste Category (DOWNTIME) | Lane Applicability | Applies When | Current Lead Time (hrs) | Current Cycle Time (hrs) | Optimized Lead Time (hrs) | Optimized Cycle Time (hrs) | %C&A | Flow Efficiency | Duration (days) | Earliest Start (day) | Earliest Finish (day) | Latest Start (day) | Latest Finish (day) | Slack (days) | Critical Path | Notes
1 | 1. Concept & Demand | Deployment artefact Approved | Cloud Ops / SRE | Platform | Collaboration |  | Approval Gate | Waiting | All lanes | Every workload | 71 | 4 | 14.4 | 2.3 | 0.76 | 0.0533 | 9.375 | 0 | 9.38 | 0 | 9.38 | 0 | Yes
2 | 1. Concept & Demand | Service record Assigned | Stream-Aligned Team | Stream-Aligned | Collaboration | 1 | Business Non-Value-Add (Type 1 Muda) | Inventory | All lanes | Every workload | 78 | 5 | 16 | 2.4 | 0.9 | 0.0602 | 10.375 | 9.38 | 19.75 | 18.88 | 29.25 | 9.5
3 | 1. Concept & Demand | Access model Confirmed | Platform Engineering | Platform | Handoff (TT anti-pattern) | 1 | Handoff | Transportation | All lanes | Every workload | 44 | 3 | 8.9 | 1.3 | 0.78 | 0.0638 | 5.875 | 9.38 | 15.25 | 23.38 | 29.25 | 14
4 | 1. Concept & Demand | Data mapping Completed | Cloud Ops / SRE | Platform | X-as-a-Service | 1 | Business Non-Value-Add (Type 1 Muda) | Waiting | Custom only | Tier 0-3 | 90 | 5 | 18.4 | 2.7 | 0.84 | 0.0526 | 11.875 | 9.38 | 21.25 | 9.38 | 21.25 | 0 | Yes
5 | 1. Concept & Demand | Design package Published | SLT | Governance Function (not a TT team) | Handoff (TT anti-pattern) | 4 | Business Non-Value-Add (Type 1 Muda) | - | All lanes | Every workload | 60 | 4 | 12.4 | 1.8 | 0.8 | 0.0625 | 8 | 21.25 | 29.25 | 21.25 | 29.25 | 0 | Yes
6 | 1. Concept & Demand | Test plan Assigned | Procurement | Governance Function (not a TT team) | Handoff (TT anti-pattern) | 2,3,5 | Approval Gate | Waiting | All lanes | Every workload | 50 | 3 | 10.3 | 1.5 | 0.69 | 0.0566 | 6.625 | 29.25 | 35.88 | 29.25 | 35.88 | 0 | Yes
7 | 1. Concept & Demand | Network path Provisioned | Resource Management | Governance Function (not a TT team) | Handoff (TT anti-pattern) | 6 | Value-Add | - | All lanes | Every workload | 62 | 4 | 12.7 | 1.9 | 0.96 | 0.0606 | 8.25 | 35.88 | 44.12 | 35.88 | 44.12 | 0 | Yes
8 | 1. Concept & Demand | Design package Published | PMO / Project Leadership | Governance Function (not a TT team) | Handoff (TT anti-pattern) | 7 | Business Non-Value-Add (Type 1 Muda) | Waiting | All lanes | Every workload | 37 | 2 | 7.6 | 1.1 | 0.83 | 0.0513 | 4.875 | 44.12 | 49 | 44.12 | 49 | 0 | Yes
9 | 1. Concept & Demand | Pattern selection Published | Cloud Platform | Platform | Collaboration | 8 | Rework Loop | Defects | All lanes | Every workload | 79 | 5 | 16.2 | 2.4 | 0.58 | 0.0595 | 10.5 | 49 | 59.5 | 49 | 59.5 | 0 | Yes
10 | 1. Concept & Demand | Test plan Drafted | Cloud Platform | Platform | X-as-a-Service | 9 | Value-Add | - | All lanes | Every workload | 67 | 4 | 13.6 | 2 | 0.9 | 0.0563 | 8.875 | 59.5 | 68.38 | 59.5 | 68.38 | 0 | Yes
11 | 1. Concept & Demand | Control evidence Executed | IAM | Complicated-Subsystem | Collaboration | 10 | Approval Gate | Waiting | Conditional | Tier 0-3 | 64 | 4 | 13.1 | 1.9 | 0.72 | 0.0588 | 8.5 | 68.38 | 76.88 | 68.38 | 76.88 | 0 | Yes
12 | 1. Concept & Demand | Readiness check Reviewed | AI Governance | Governance Function (not a TT team) | Collaboration | 11 | Rework Loop | Defects | All lanes | Every workload | 93 | 6 | 19.1 | 2.8 | 0.56 | 0.0606 | 12.375 | 76.88 | 89.25 | 76.88 | 89.25 | 0 | Yes
13 | 1. Concept & Demand | Test plan Signed off | SLT | Governance Function (not a TT team) | Handoff (TT anti-pattern) | 11,12 | Approval Gate | Waiting | All lanes | Every workload | 88 | 5 | 17.9 | 2.7 | 0.78 | 0.0538 | 11.625 | 89.25 | 100.88 | 89.25 | 100.88 | 0 | Yes
14 | 1. Concept & Demand | Service record Submitted | Cloud Ops / SRE | Platform | Collaboration | 13 | Approval Gate | Waiting | All lanes | Every workload | 43 | 3 | 8.9 | 1.3 | 0.58 | 0.0652 | 5.75 | 100.88 | 106.62 | 100.88 | 106.62 | 0 | Yes
15 | 2. Discovery & Product Selection | Data mapping Signed off | Delivery Leadership | Stream-Aligned | Collaboration | 14 | Approval Gate | Waiting | All lanes | Every workload | 167 | 30 | 51.7 | 18 | 0.57 | 0.1523 | 24.625 | 106.62 | 131.25 | 106.62 | 131.25 | 0 | Yes
16 | 2. Discovery & Product Selection | Design package Documented | Platform Engineering | Platform | X-as-a-Service | 15 | Value-Add | - | All lanes | Every workload | 94 | 17 | 29.2 | 10.2 | 0.95 | 0.1532 | 13.875 | 131.25 | 145.12 | 131.25 | 145.12 | 0 | Yes
17 | 2. Discovery & Product Selection | Readiness check Published | Architecture Governance | Governance Function (not a TT team) | Handoff (TT anti-pattern) | 16 | Value-Add | - | All lanes | Every workload | 198 | 36 | 61.5 | 21.5 | 0.87 | 0.1538 | 29.25 | 145.12 | 174.38 | 145.12 | 174.38 | 0 | Yes
18 | 2. Discovery & Product Selection | Service record Signed off | Procurement / Legal | Governance Function (not a TT team) | Handoff (TT anti-pattern) | 17 | Value-Add | - | Standard + Custom | Azure workloads | 141 | 25 | 43.9 | 15.3 | 0.8 | 0.1506 | 20.75 | 174.38 | 195.12 | 174.38 | 195.12 | 0 | Yes
19 | 2. Discovery & Product Selection | Intake record Approved | Database Platforms | Complicated-Subsystem | X-as-a-Service | 15 | Business Non-Value-Add (Type 1 Muda) | Extra-Processing | All lanes | Every workload | 101 | 18 | 31.2 | 10.9 | 0.74 | 0.1513 | 14.875 | 131.25 | 146.12 | 195.62 | 210.5 | 64.38
20 | 2. Discovery & Product Selection | Cost model Confirmed | Cloud Platform | Platform | X-as-a-Service | 18 | Value-Add | - | All lanes | Every workload | 104 | 19 | 32.2 | 11.2 | 0.96 | 0.1545 | 15.375 | 195.12 | 210.5 | 195.12 | 210.5 | 0 | Yes
21 | 2. Discovery & Product Selection | Network path Signed off | Cloud FinOps | Platform | X-as-a-Service | 15 | Value-Add | - | All lanes | Every workload | 149 | 27 | 46.3 | 16.2 | 0.92 | 0.1534 | 22 | 131.25 | 153.25 | 188.5 | 210.5 | 57.25
22 | 2. Discovery & Product Selection | Pattern selection Drafted | Platform Team | Platform | Collaboration | 20,19,21 | Approval Gate | Waiting | All lanes | Every workload | 104 | 19 | 32.3 | 11.3 | 0.7 | 0.1545 | 15.375 | 210.5 | 225.88 | 210.5 | 225.88 | 0 | Yes
23 | 2. Discovery & Product Selection | Data mapping Configured | IAM | Complicated-Subsystem | X-as-a-Service | 22 | Business Non-Value-Add (Type 1 Muda) | Waiting | All lanes | Every workload | 94 | 17 | 29.3 | 10.2 | 0.73 | 0.1532 | 13.875 | 225.88 | 239.75 | 225.88 | 239.75 | 0 | Yes
24 | 3. Placement & Pattern Selection | Cost model Documented | Resilience Architecture | Complicated-Subsystem | Collaboration | 22,23 | Approval Gate | Waiting | Standard + Custom | Azure workloads | 28 | 3 | 8 | 1.7 | 0.61 | 0.0968 | 3.875 | 239.75 | 243.62 | 239.75 | 243.62 | 0 | Yes
25 | 3. Placement & Pattern Selection | Pattern selection Submitted | Cloud Platform | Platform | Collaboration | 24 | Approval Gate | Waiting | All lanes | Every workload | 29 | 3 | 8.5 | 1.8 | 0.68 | 0.0938 | 4 | 243.62 | 247.62 | 243.62 | 247.62 | 0 | Yes
26 | 3. Placement & Pattern Selection | Pattern selection Configured | Network Security | Complicated-Subsystem | Collaboration | 25 | Approval Gate | Waiting | Standard + Custom | Regulated / personal data | 29 | 3 | 8.4 | 1.8 | 0.76 | 0.0938 | 4 | 247.62 | 251.62 | 247.62 | 251.62 | 0 | Yes
27 | 3. Placement & Pattern Selection | Control evidence Configured | PMO / Project Leadership | Governance Function (not a TT team) | Handoff (TT anti-pattern) | 26 | Approval Gate | Waiting | All lanes | Every workload | 33 | 3 | 9.5 | 2 | 0.6 | 0.0833 | 4.5 | 251.62 | 256.12 | 251.62 | 256.12 | 0 | Yes
28 | 3. Placement & Pattern Selection | Risk assessment Published | PMO / Project Leadership | Governance Function (not a TT team) | Handoff (TT anti-pattern) | 27 | Business Non-Value-Add (Type 1 Muda) | Extra-Processing | All lanes | Every workload | 32 | 3 | 9.3 | 2 | 0.86 | 0.0857 | 4.375 | 256.12 | 260.5 | 256.12 | 260.5 | 0 | Yes
29 | 3. Placement & Pattern Selection | Test plan Onboarded | Integration Platforms | Complicated-Subsystem | X-as-a-Service | 27 | Value-Add | - | All lanes | Every workload | 47 | 4 | 13.5 | 2.8 | 0.94 | 0.0784 | 6.375 | 256.12 | 262.5 | 258.12 | 264.5 | 2
30 | 3. Placement & Pattern Selection | Test plan Executed | SLT | Governance Function (not a TT team) | Handoff (TT anti-pattern) | 28 | Value-Add | - | Standard + Custom | Regulated / personal data | 29 | 3 | 8.3 | 1.8 | 0.82 | 0.0938 | 4 | 260.5 | 264.5 | 260.5 | 264.5 | 0 | Yes
31 | 3. Placement & Pattern Selection | Control evidence Drafted | Procurement | Governance Function (not a TT team) | Handoff (TT anti-pattern) | 27 | Business Non-Value-Add (Type 1 Muda) | Waiting | All lanes | Every workload | 45 | 4 | 12.9 | 2.7 | 0.9 | 0.0816 | 6.125 | 256.12 | 262.25 | 258.38 | 264.5 | 2.25
32 | 4. Requirements & Classification | Control evidence Confirmed | Platform Team | Platform | X-as-a-Service | 30,29,31 | Value-Add | - | All lanes | Every workload | 22 | 3 | 7.6 | 1.8 | 0.85 | 0.12 | 3.125 | 264.5 | 267.62 | 264.5 | 267.62 | 0 | Yes
33 | 4. Requirements & Classification | Pattern selection Provisioned | CMDB / Asset Mgmt | Platform | X-as-a-Service | 32 | Value-Add | - | All lanes | Every workload | 40 | 5 | 13.3 | 3.2 | 0.87 | 0.1111 | 5.625 | 267.62 | 273.25 | 267.62 | 273.25 | 0 | Yes
34 | 4. Requirements & Classification | Design package Documented | AI Governance | Governance Function (not a TT team) | Handoff (TT anti-pattern) | 33 | Value-Add | - | All lanes | Every workload | 48 | 6 | 16.1 | 3.9 | 0.91 | 0.1111 | 6.75 | 273.25 | 280 | 273.25 | 280 | 0 | Yes
35 | 4. Requirements & Classification | Readiness check Provisioned | AI Governance Board | Governance Function (not a TT team) | Handoff (TT anti-pattern) | 34 | Business Non-Value-Add (Type 1 Muda) | - | All lanes | Every workload | 49 | 6 | 16.4 | 4 | 0.81 | 0.1091 | 6.875 | 280 | 286.88 | 280 | 286.88 | 0 | Yes
36 | 4. Requirements & Classification | Network path Onboarded | Solution Architecture | Enabling | Facilitating | 35 | Value-Add | - | All lanes | Every workload | 45 | 5 | 14.9 | 3.6 | 0.83 | 0.1 | 6.25 | 286.88 | 293.12 | 286.88 | 293.12 | 0 | Yes
37 | 4. Requirements & Classification | Network path Completed | Cloud FinOps | Platform | Collaboration | 36 | Approval Gate | Waiting | Custom only | Internet-facing only | 46 | 6 | 15.4 | 3.7 | 0.68 | 0.1154 | 6.5 | 293.12 | 299.62 | 293.12 | 299.62 | 0 | Yes
38 | 4. Requirements & Classification | Data mapping Assigned | Resilience Architecture | Complicated-Subsystem | X-as-a-Service | 37 | Business Non-Value-Add (Type 1 Muda) | Waiting | All lanes | Every workload | 51 | 6 | 17.1 | 4.2 | 0.92 | 0.1053 | 7.125 | 299.62 | 306.75 | 300.38 | 307.5 | 0.75
39 | 4. Requirements & Classification | Cost model Validated | Database Platforms | Complicated-Subsystem | X-as-a-Service | 37 | Value-Add | - | All lanes | Every workload | 54 | 7 | 18 | 4.4 | 0.96 | 0.1148 | 7.625 | 299.62 | 307.25 | 299.62 | 307.25 | 0 | Yes
40 | 4. Requirements & Classification | Intake record Onboarded | AI Governance Board | Governance Function (not a TT team) | Handoff (TT anti-pattern) | 39 | Value-Add | - | All lanes | Every workload | 23 | 3 | 7.7 | 1.9 | 0.86 | 0.1154 | 3.25 | 307.25 | 310.5 | 307.25 | 310.5 | 0 | Yes
41 | 4. Requirements & Classification | Network path Submitted | Business / Product Owner | Stream-Aligned | Collaboration | 38 | Business Non-Value-Add (Type 1 Muda) | Extra-Processing | All lanes | Every workload | 21 | 3 | 6.9 | 1.7 | 0.83 | 0.125 | 3 | 306.75 | 309.75 | 307.5 | 310.5 | 0.75
42 | 4. Requirements & Classification | Cost model Completed | Platform Engineering | Platform | X-as-a-Service | 37 | Value-Add | - | Custom only | Regulated / personal data | 24 | 3 | 8.2 | 2 | 0.94 | 0.1111 | 3.375 | 299.62 | 303 | 307.12 | 310.5 | 7.5
43 | 4. Requirements & Classification | Intake record Confirmed | Solution Architecture | Enabling | Collaboration | 40,41,42 | Approval Gate | Waiting | All lanes | Every workload | 25 | 3 | 8.4 | 2 | 0.62 | 0.1071 | 3.5 | 310.5 | 314 | 310.5 | 314 | 0 | Yes
44 | 5. Architecture & Design | Access model Executed | Database Platforms | Complicated-Subsystem | X-as-a-Service | 43 | Value-Add | - | All lanes | Every workload | 47 | 6 | 15.1 | 3.9 | 0.97 | 0.1132 | 6.625 | 314 | 320.62 | 314 | 320.62 | 0 | Yes
45 | 5. Architecture & Design | Service record Completed | Cybersecurity | Complicated-Subsystem | X-as-a-Service | 44 | Business Non-Value-Add (Type 1 Muda) | Extra-Processing | Custom only | Migrations only | 50 | 7 | 16.4 | 4.2 | 0.87 | 0.1228 | 7.125 | 320.62 | 327.75 | 320.62 | 327.75 | 0 | Yes
46 | 5. Architecture & Design | Service record Onboarded | Cloud Ops / SRE | Platform | X-as-a-Service | 45 | Value-Add | - | All lanes | Every workload | 51 | 7 | 16.7 | 4.3 | 0.85 | 0.1207 | 7.25 | 327.75 | 335 | 327.75 | 335 | 0 | Yes
47 | 5. Architecture & Design | Pattern selection Approved | Finance / PMO | Governance Function (not a TT team) | Handoff (TT anti-pattern) | 46 | Value-Add | - | All lanes | Every workload | 24 | 3 | 7.7 | 2 | 0.83 | 0.1111 | 3.375 | 335 | 338.38 | 335 | 338.38 | 0 | Yes
48 | 5. Architecture & Design | Network path Executed | Network Engineering | Complicated-Subsystem | X-as-a-Service | 44 | Value-Add | - | Conditional | GenAI use cases | 26 | 4 | 8.6 | 2.2 | 0.83 | 0.1333 | 3.75 | 320.62 | 324.38 | 333 | 336.75 | 12.38
49 | 5. Architecture & Design | Design package Configured | Cloud Ops / SRE | Platform | X-as-a-Service | 47 | Value-Add | - | All lanes | Every workload | 27 | 4 | 8.9 | 2.3 | 0.82 | 0.129 | 3.875 | 338.38 | 342.25 | 338.38 | 342.25 | 0 | Yes
50 | 5. Architecture & Design | Access model Drafted | Database Platforms | Complicated-Subsystem | Collaboration | 44 | Rework Loop | Defects | All lanes | Every workload | 40 | 6 | 13 | 3.4 | 0.63 | 0.1304 | 5.75 | 320.62 | 326.38 | 328 | 333.75 | 7.38
51 | 5. Architecture & Design | Access model Configured | Cloud Platform | Platform | X-as-a-Service | 50 | Value-Add | - | Conditional | Tier 0-3 | 32 | 4 | 10.5 | 2.7 | 0.92 | 0.1111 | 4.5 | 326.38 | 330.88 | 333.75 | 338.25 | 7.38
52 | 5. Architecture & Design | Risk assessment Published | AI Governance | Governance Function (not a TT team) | Handoff (TT anti-pattern) | 44 | Value-Add | - | All lanes | Every workload | 51 | 7 | 16.6 | 4.3 | 0.94 | 0.1207 | 7.25 | 320.62 | 327.88 | 335 | 342.25 | 14.38
53 | 5. Architecture & Design | Cost model Onboarded | IAM | Complicated-Subsystem | X-as-a-Service | 51 | Value-Add | - | All lanes | Every workload | 28 | 4 | 9.2 | 2.4 | 0.92 | 0.125 | 4 | 330.88 | 334.88 | 338.25 | 342.25 | 7.38
54 | 5. Architecture & Design | Network path Submitted | Network Engineering | Complicated-Subsystem | X-as-a-Service | 48 | Value-Add | - | All lanes | Every workload | 39 | 5 | 12.7 | 3.3 | 0.81 | 0.1136 | 5.5 | 324.38 | 329.88 | 336.75 | 342.25 | 12.38
55 | 5. Architecture & Design | Readiness check Documented | Resilience Architecture | Complicated-Subsystem | Collaboration | 54,49,53,52 | Approval Gate | Waiting | Standard + Custom | Azure workloads | 50 | 7 | 16.3 | 4.2 | 0.74 | 0.1228 | 7.125 | 342.25 | 349.38 | 342.25 | 349.38 | 0 | Yes
56 | 5. Architecture & Design | Cost model Assigned | PMO / Project Leadership | Governance Function (not a TT team) | Handoff (TT anti-pattern) | 55 | Value-Add | - | All lanes | Every workload | 27 | 4 | 8.9 | 2.3 | 0.89 | 0.129 | 3.875 | 349.38 | 353.25 | 354.25 | 358.12 | 4.88
57 | 5. Architecture & Design | Data mapping Drafted | IAM | Complicated-Subsystem | X-as-a-Service | 55 | Value-Add | - | Custom only | Buy or SaaS only | 45 | 6 | 14.6 | 3.8 | 0.97 | 0.1176 | 6.375 | 349.38 | 355.75 | 349.38 | 355.75 | 0 | Yes
58 | 5. Architecture & Design | Design package Onboarded | Cloud Platform | Platform | X-as-a-Service | 56 | Value-Add | - | All lanes | Every workload | 27 | 4 | 8.6 | 2.2 | 0.96 | 0.129 | 3.875 | 353.25 | 357.12 | 358.12 | 362 | 4.88
59 | 5. Architecture & Design | Runbook Confirmed | Finance / PMO | Governance Function (not a TT team) | Handoff (TT anti-pattern) | 57 | Business Non-Value-Add (Type 1 Muda) | Extra-Processing | All lanes | Every workload | 44 | 6 | 14.2 | 3.7 | 0.76 | 0.12 | 6.25 | 355.75 | 362 | 355.75 | 362 | 0 | Yes
60 | 6. Architecture Governance | Cost model Drafted | Finance / PMO | Governance Function (not a TT team) | Handoff (TT anti-pattern) | 59,58 | Approval Gate | Waiting | All lanes | Every workload | 46 | 2 | 9.6 | 1.1 | 0.75 | 0.0417 | 6 | 362 | 368 | 362 | 368 | 0 | Yes
61 | 6. Architecture Governance | Design package Reviewed | Cloud FinOps | Platform | Collaboration | 60 | Approval Gate | Waiting | All lanes | Every workload | 47 | 2 | 9.5 | 1.2 | 0.67 | 0.0408 | 6.125 | 368 | 374.12 | 368 | 374.12 | 0 | Yes
62 | 6. Architecture Governance | Network path Signed off | Platform Engineering | Platform | Collaboration | 61 | Approval Gate | Waiting | Custom only | Migrations only | 80 | 4 | 16.4 | 2 | 0.71 | 0.0476 | 10.5 | 374.12 | 384.62 | 374.12 | 384.62 | 0 | Yes
63 | 6. Architecture Governance | Data mapping Onboarded | Enabling Architecture | Enabling | Collaboration | 62 | Approval Gate | Waiting | All lanes | Every workload | 92 | 5 | 18.8 | 2.3 | 0.8 | 0.0515 | 12.125 | 384.62 | 396.75 | 384.62 | 396.75 | 0 | Yes
64 | 6. Architecture Governance | Access model Reviewed | Network Engineering | Complicated-Subsystem | Collaboration | 63 | Approval Gate | Waiting | All lanes | Every workload | 61 | 3 | 12.4 | 1.5 | 0.58 | 0.0469 | 8 | 396.75 | 404.75 | 396.75 | 404.75 | 0 | Yes
65 | 6. Architecture Governance | Design package Confirmed | Data Privacy | Complicated-Subsystem | X-as-a-Service | 64 | Value-Add | - | Standard + Custom | Tier 0-3 | 74 | 4 | 15.3 | 1.9 | 0.84 | 0.0513 | 9.75 | 404.75 | 414.5 | 404.75 | 414.5 | 0 | Yes
66 | 7. Procurement & Vendor | Network path Documented | AI Governance | Governance Function (not a TT team) | Handoff (TT anti-pattern) | 65 | Business Non-Value-Add (Type 1 Muda) | Extra-Processing | All lanes | Every workload | 138 | 8 | 32.9 | 3.9 | 0.72 | 0.0548 | 18.25 | 414.5 | 432.75 | 414.5 | 432.75 | 0 | Yes
67 | 7. Procurement & Vendor | Readiness check Provisioned | Resilience Architecture | Complicated-Subsystem | X-as-a-Service | 66 | Value-Add | - | All lanes | Every workload | 191 | 10 | 45.5 | 5.3 | 0.85 | 0.0498 | 25.125 | 432.75 | 457.88 | 432.75 | 457.88 | 0 | Yes
68 | 7. Procurement & Vendor | Network path Onboarded | Cloud FinOps | Platform | X-as-a-Service | 66 | Business Non-Value-Add (Type 1 Muda) | Extra-Processing | Custom only | Buy or SaaS only | 102 | 6 | 24.3 | 2.9 | 0.75 | 0.0556 | 13.5 | 432.75 | 446.25 | 444.38 | 457.88 | 11.62
69 | 7. Procurement & Vendor | Data mapping Approved | CMDB / Asset Mgmt | Platform | Collaboration | 66,67,68 | Approval Gate | Waiting | All lanes | Every workload | 147 | 8 | 35.1 | 4.1 | 0.72 | 0.0516 | 19.375 | 457.88 | 477.25 | 457.88 | 477.25 | 0 | Yes
70 | 7. Procurement & Vendor | Access model Assigned | AI Governance Board | Governance Function (not a TT team) | Handoff (TT anti-pattern) | 69 | Value-Add | - | Custom only | Internet-facing only | 102 | 6 | 24.2 | 2.8 | 0.86 | 0.0556 | 13.5 | 477.25 | 490.75 | 477.25 | 490.75 | 0 | Yes
71 | 8. Security & Privacy Approvals | Readiness check Provisioned | Cloud FinOps | Platform | Collaboration | 69,70 | Approval Gate | Waiting | Standard + Custom | Internet-facing only | 72 | 4 | 14.6 | 2 | 0.73 | 0.0526 | 9.5 | 490.75 | 500.25 | 490.75 | 500.25 | 0 | Yes
72 | 8. Security & Privacy Approvals | Intake record Submitted | Data Privacy | Complicated-Subsystem | Collaboration | 71 | Approval Gate | Waiting | All lanes | Every workload | 80 | 4 | 16.4 | 2.2 | 0.57 | 0.0476 | 10.5 | 500.25 | 510.75 | 500.25 | 510.75 | 0 | Yes
73 | 8. Security & Privacy Approvals | Cost model Published | Cloud Platform | Platform | Collaboration | 72 | Approval Gate | Waiting | Conditional | Migrations only | 123 | 7 | 25.4 | 3.4 | 0.74 | 0.0538 | 16.25 | 510.75 | 527 | 510.75 | 527 | 0 | Yes
74 | 8. Security & Privacy Approvals | Pattern selection Completed | Finance / PMO | Governance Function (not a TT team) | Handoff (TT anti-pattern) | 73 | Value-Add | - | All lanes | Every workload | 85 | 5 | 17.6 | 2.4 | 0.87 | 0.0556 | 11.25 | 527 | 538.25 | 527 | 538.25 | 0 | Yes
75 | 9. Provisioning (Pipeline / IaC) | Risk assessment Configured | Delivery Leadership | Stream-Aligned | Collaboration | 73,74 | Value-Add | - | All lanes | Every workload | 40 | 5 | 13.2 | 3.4 | 0.91 | 0.1111 | 5.625 | 538.25 | 543.88 | 538.25 | 543.88 | 0 | Yes
76 | 9. Provisioning (Pipeline / IaC) | Exception request Provisioned | Network Security | Complicated-Subsystem | X-as-a-Service | 75 | Business Non-Value-Add (Type 1 Muda) | Inventory | All lanes | Every workload | 46 | 6 | 15.3 | 3.9 | 0.83 | 0.1154 | 6.5 | 543.88 | 550.38 | 557.75 | 564.25 | 13.88
77 | 9. Provisioning (Pipeline / IaC) | Network path Documented | IT Change Management | Governance Function (not a TT team) | Handoff (TT anti-pattern) | 75 | Business Non-Value-Add (Type 1 Muda) | Extra-Processing | Standard + Custom | GenAI use cases | 33 | 4 | 11 | 2.8 | 0.7 | 0.1081 | 4.625 | 543.88 | 548.5 | 550.5 | 555.12 | 6.62
78 | 9. Provisioning (Pipeline / IaC) | Data mapping Executed | Architecture Governance | Governance Function (not a TT team) | Handoff (TT anti-pattern) | 77 | Value-Add | - | Custom only | Azure workloads | 65 | 8 | 21.3 | 5.4 | 0.96 | 0.1096 | 9.125 | 548.5 | 557.62 | 555.12 | 564.25 | 6.62
79 | 9. Provisioning (Pipeline / IaC) | Risk assessment Confirmed | Resilience Architecture | Complicated-Subsystem | X-as-a-Service | 75 | Business Non-Value-Add (Type 1 Muda) | Waiting | All lanes | Every workload | 32 | 4 | 10.4 | 2.6 | 0.71 | 0.1111 | 4.5 | 543.88 | 548.38 | 543.88 | 548.38 | 0 | Yes
80 | 9. Provisioning (Pipeline / IaC) | Test plan Validated | Procurement | Governance Function (not a TT team) | Handoff (TT anti-pattern) | 79 | Business Non-Value-Add (Type 1 Muda) | Waiting | Standard + Custom | Tier 0-3 | 44 | 6 | 14.4 | 3.7 | 0.89 | 0.12 | 6.25 | 548.38 | 554.62 | 548.38 | 554.62 | 0 | Yes
81 | 9. Provisioning (Pipeline / IaC) | Service record Submitted | Network Engineering | Complicated-Subsystem | X-as-a-Service | 75 | Value-Add | - | Conditional | Tier 0-3 | 37 | 5 | 12.3 | 3.1 | 0.81 | 0.119 | 5.25 | 543.88 | 549.12 | 559 | 564.25 | 15.12
82 | 9. Provisioning (Pipeline / IaC) | Cost model Onboarded | Resource Management | Governance Function (not a TT team) | Handoff (TT anti-pattern) | 80 | Value-Add | - | Custom only | Azure workloads | 68 | 9 | 22.4 | 5.7 | 0.85 | 0.1169 | 9.625 | 554.62 | 564.25 | 554.62 | 564.25 | 0 | Yes
83 | 9. Provisioning (Pipeline / IaC) | Pattern selection Provisioned | Architecture Governance | Governance Function (not a TT team) | Handoff (TT anti-pattern) | 76,78,82,81 | Approval Gate | Waiting | All lanes | Every workload | 47 | 6 | 15.3 | 3.9 | 0.6 | 0.1132 | 6.625 | 564.25 | 570.88 | 564.25 | 570.88 | 0 | Yes
84 | 10. Platform & Middleware Integration | Cost model Provisioned | Solution Architecture | Enabling | Facilitating | 83 | Value-Add | - | Custom only | Internet-facing only | 44 | 4 | 15 | 2.4 | 0.9 | 0.0833 | 6 | 570.88 | 576.88 | 570.88 | 576.88 | 0 | Yes
85 | 10. Platform & Middleware Integration | Network path Configured | Solution Architecture | Enabling | Facilitating | 84 | Business Non-Value-Add (Type 1 Muda) | - | All lanes | Every workload | 44 | 4 | 15 | 2.3 | 0.8 | 0.0833 | 6 | 576.88 | 582.88 | 576.88 | 582.88 | 0 | Yes
86 | 10. Platform & Middleware Integration | Risk assessment Submitted | Procurement / Legal | Governance Function (not a TT team) | Handoff (TT anti-pattern) | 84 | Value-Add | - | All lanes | Every workload | 59 | 5 | 20.4 | 3.1 | 0.96 | 0.0781 | 8 | 576.88 | 584.88 | 587.38 | 595.38 | 10.5
87 | 10. Platform & Middleware Integration | Risk assessment Confirmed | Finance / PMO | Governance Function (not a TT team) | Handoff (TT anti-pattern) | 84 | Value-Add | - | Standard + Custom | Non-standard decisions | 33 | 3 | 11.2 | 1.7 | 0.9 | 0.0833 | 4.5 | 576.88 | 581.38 | 583.25 | 587.75 | 6.38
88 | 10. Platform & Middleware Integration | Access model Approved | PMO / Demand Mgmt | Governance Function (not a TT team) | Handoff (TT anti-pattern) | 84 | Value-Add | - | Custom only | Internet-facing only | 73 | 6 | 25.1 | 3.9 | 0.91 | 0.0759 | 9.875 | 576.88 | 586.75 | 587.25 | 597.12 | 10.38
89 | 10. Platform & Middleware Integration | Access model Signed off | PMO / Demand Mgmt | Governance Function (not a TT team) | Handoff (TT anti-pattern) | 85 | Business Non-Value-Add (Type 1 Muda) | Inventory | All lanes | Every workload | 50 | 4 | 17.2 | 2.6 | 0.71 | 0.0741 | 6.75 | 582.88 | 589.62 | 582.88 | 589.62 | 0 | Yes
90 | 10. Platform & Middleware Integration | Network path Published | AI Governance | Governance Function (not a TT team) | Handoff (TT anti-pattern) | 89 | Value-Add | - | All lanes | Every workload | 59 | 5 | 20.1 | 3.1 | 0.93 | 0.0781 | 8 | 589.62 | 597.62 | 589.62 | 597.62 | 0 | Yes
91 | 10. Platform & Middleware Integration | Service record Configured | Architecture Governance | Governance Function (not a TT team) | Handoff (TT anti-pattern) | 90 | Value-Add | - | All lanes | Every workload | 48 | 4 | 16.3 | 2.5 | 0.94 | 0.0769 | 6.5 | 597.62 | 604.12 | 597.62 | 604.12 | 0 | Yes
92 | 10. Platform & Middleware Integration | Intake record Submitted | Platform Engineering | Platform | X-as-a-Service | 88 | Business Non-Value-Add (Type 1 Muda) | - | All lanes | Every workload | 52 | 4 | 17.9 | 2.8 | 0.73 | 0.0714 | 7 | 586.75 | 593.75 | 597.12 | 604.12 | 10.38
93 | 10. Platform & Middleware Integration | Network path Confirmed | IT Change Management | Governance Function (not a TT team) | Handoff (TT anti-pattern) | 86 | Value-Add | - | Standard + Custom | Non-standard decisions | 65 | 5 | 22.4 | 3.4 | 0.85 | 0.0714 | 8.75 | 584.88 | 593.62 | 595.38 | 604.12 | 10.5
94 | 10. Platform & Middleware Integration | Deployment artefact Drafted | Architecture Governance | Governance Function (not a TT team) | Handoff (TT anti-pattern) | 87 | Business Non-Value-Add (Type 1 Muda) | - | All lanes | Every workload | 63 | 5 | 21.5 | 3.3 | 0.88 | 0.0735 | 8.5 | 581.38 | 589.88 | 587.75 | 596.25 | 6.38
95 | 10. Platform & Middleware Integration | Network path Published | CMDB / Asset Mgmt | Platform | X-as-a-Service | 94 | Business Non-Value-Add (Type 1 Muda) | Waiting | All lanes | Every workload | 58 | 5 | 19.9 | 3.1 | 0.71 | 0.0794 | 7.875 | 589.88 | 597.75 | 596.25 | 604.12 | 6.38
96 | 11. Network & Connectivity | Pattern selection Approved | Platform Engineering | Platform | X-as-a-Service | 93,91,95,92 | Value-Add | - | Conditional | Buy or SaaS only | 24 | 2 | 5.5 | 0.8 | 0.89 | 0.0769 | 3.25 | 604.12 | 607.38 | 604.12 | 607.38 | 0 | Yes
97 | 11. Network & Connectivity | Test plan Submitted | Data Privacy | Complicated-Subsystem | Handoff (TT anti-pattern) | 96 | Handoff | Transportation | All lanes | Every workload | 27 | 2 | 6 | 0.9 | 0.63 | 0.069 | 3.625 | 607.38 | 611 | 607.38 | 611 | 0 | Yes
98 | 11. Network & Connectivity | Risk assessment Submitted | AI Governance Board | Governance Function (not a TT team) | Handoff (TT anti-pattern) | 97 | Value-Add | - | Standard + Custom | Non-standard decisions | 51 | 3 | 11.5 | 1.6 | 0.86 | 0.0556 | 6.75 | 611 | 617.75 | 611 | 617.75 | 0 | Yes
99 | 11. Network & Connectivity | Risk assessment Signed off | Network Security | Complicated-Subsystem | X-as-a-Service | 98 | Value-Add | - | All lanes | Every workload | 41 | 3 | 9.2 | 1.3 | 0.96 | 0.0682 | 5.5 | 617.75 | 623.25 | 617.75 | 623.25 | 0 | Yes
100 | 11. Network & Connectivity | Cost model Published | Database Platforms | Complicated-Subsystem | Collaboration | 99 | Approval Gate | Waiting | All lanes | Every workload | 37 | 2 | 8.2 | 1.2 | 0.76 | 0.0513 | 4.875 | 623.25 | 628.12 | 623.25 | 628.12 | 0 | Yes
101 | 12. Data | Test plan Configured | PMO / Project Leadership | Governance Function (not a TT team) | Handoff (TT anti-pattern) | 100 | Value-Add | - | All lanes | Every workload | 57 | 11 | 21.4 | 7.2 | 0.9 | 0.1618 | 8.5 | 628.12 | 636.62 | 628.12 | 636.62 | 0 | Yes
102 | 12. Data | Intake record Signed off | AI Governance | Governance Function (not a TT team) | Handoff (TT anti-pattern) | 101 | Value-Add | - | All lanes | Every workload | 31 | 6 | 11.8 | 4 | 0.9 | 0.1622 | 4.625 | 636.62 | 641.25 | 640.25 | 644.88 | 3.62
103 | 12. Data | Test plan Provisioned | Enabling Architecture | Enabling | Facilitating | 101 | Business Non-Value-Add (Type 1 Muda) | Inventory | Custom only | Regulated / personal data | 56 | 10 | 20.8 | 7.1 | 0.74 | 0.1515 | 8.25 | 636.62 | 644.88 | 636.62 | 644.88 | 0 | Yes
104 | 13. Observability & Ops Readiness | Access model Validated | Finance / PMO | Governance Function (not a TT team) | Handoff (TT anti-pattern) | 102,103 | Approval Gate | Waiting | Standard + Custom | Internet-facing only | 27 | 3 | 7.7 | 1.8 | 0.77 | 0.1 | 3.75 | 644.88 | 648.62 | 644.88 | 648.62 | 0 | Yes
105 | 13. Observability & Ops Readiness | Risk assessment Reviewed | Resilience Architecture | Complicated-Subsystem | X-as-a-Service | 104 | Value-Add | - | Standard + Custom | Regulated / personal data | 26 | 3 | 7.4 | 1.7 | 0.91 | 0.1034 | 3.625 | 648.62 | 652.25 | 656.62 | 660.25 | 8
106 | 13. Observability & Ops Readiness | Cost model Configured | AI Governance | Governance Function (not a TT team) | Collaboration | 104 | Rework Loop | Defects | All lanes | Every workload | 32 | 4 | 9.2 | 2.1 | 0.4 | 0.1111 | 4.5 | 648.62 | 653.12 | 648.62 | 653.12 | 0 | Yes
107 | 13. Observability & Ops Readiness | Access model Submitted | Solution Architecture | Enabling | Facilitating | 106 | Value-Add | - | Custom only | Regulated / personal data | 42 | 5 | 12.2 | 2.8 | 0.93 | 0.1064 | 5.875 | 653.12 | 659 | 653.12 | 659 | 0 | Yes
108 | 13. Observability & Ops Readiness | Design package Executed | PMO / Demand Mgmt | Governance Function (not a TT team) | Handoff (TT anti-pattern) | 105 | Business Non-Value-Add (Type 1 Muda) | Waiting | Custom only | GenAI use cases | 36 | 4 | 10.3 | 2.4 | 0.71 | 0.1 | 5 | 652.25 | 657.25 | 660.25 | 665.25 | 8
109 | 13. Observability & Ops Readiness | Runbook Onboarded | Integration Platforms | Complicated-Subsystem | X-as-a-Service | 107 | Value-Add | - | Custom only | Non-standard decisions | 45 | 5 | 12.8 | 3 | 0.91 | 0.1 | 6.25 | 659 | 665.25 | 659 | 665.25 | 0 | Yes
110 | 14. Test & Validation | Readiness check Onboarded | Solution Architecture | Enabling | Facilitating | 104,108,109 | Value-Add | - | All lanes | Every workload | 54 | 9 | 15.1 | 5.1 | 0.87 | 0.1429 | 7.875 | 665.25 | 673.12 | 665.25 | 673.12 | 0 | Yes
111 | 14. Test & Validation | Runbook Executed | Data Privacy | Complicated-Subsystem | X-as-a-Service | 110 | Business Non-Value-Add (Type 1 Muda) | Extra-Processing | All lanes | Every workload | 39 | 6 | 10.6 | 3.6 | 0.74 | 0.1333 | 5.625 | 673.12 | 678.75 | 673.75 | 679.38 | 0.62
112 | 14. Test & Validation | Test plan Drafted | Cybersecurity | Complicated-Subsystem | X-as-a-Service | 110 | Value-Add | - | All lanes | Every workload | 43 | 7 | 11.8 | 4.1 | 0.98 | 0.14 | 6.25 | 673.12 | 679.38 | 673.12 | 679.38 | 0 | Yes
113 | 14. Test & Validation | Risk assessment Executed | PMO / Demand Mgmt | Governance Function (not a TT team) | Handoff (TT anti-pattern) | 110,111,112 | Approval Gate | Waiting | All lanes | Every workload | 51 | 8 | 13.9 | 4.8 | 0.75 | 0.1356 | 7.375 | 679.38 | 686.75 | 679.38 | 686.75 | 0 | Yes
114 | 14. Test & Validation | Service record Signed off | Network Security | Complicated-Subsystem | Collaboration | 113 | Approval Gate | Waiting | Custom only | Non-standard decisions | 80 | 13 | 21.9 | 7.5 | 0.79 | 0.1398 | 11.625 | 686.75 | 698.38 | 686.75 | 698.38 | 0 | Yes
115 | 14. Test & Validation | Risk assessment Executed | AI Governance Board | Governance Function (not a TT team) | Handoff (TT anti-pattern) | 114 | Business Non-Value-Add (Type 1 Muda) | Waiting | All lanes | Every workload | 58 | 10 | 15.9 | 5.4 | 0.86 | 0.1471 | 8.5 | 698.38 | 706.88 | 713 | 721.5 | 14.62
116 | 14. Test & Validation | Deployment artefact Completed | IT Change Management | Governance Function (not a TT team) | Handoff (TT anti-pattern) | 114 | Value-Add | - | All lanes | Every workload | 68 | 11 | 18.6 | 6.4 | 0.85 | 0.1392 | 9.875 | 698.38 | 708.25 | 711.62 | 721.5 | 13.25
117 | 14. Test & Validation | Pattern selection Onboarded | Architecture Governance | Governance Function (not a TT team) | Handoff (TT anti-pattern) | 114 | Value-Add | - | Standard + Custom | Non-standard decisions | 92 | 15 | 25.2 | 8.6 | 0.82 | 0.1402 | 13.375 | 698.38 | 711.75 | 698.38 | 711.75 | 0 | Yes
118 | 14. Test & Validation | Network path Configured | CMDB / Asset Mgmt | Platform | Collaboration | 117 | Rework Loop | Defects | Conditional | Regulated / personal data | 67 | 11 | 18.5 | 6.3 | 0.44 | 0.141 | 9.75 | 711.75 | 721.5 | 711.75 | 721.5 | 0 | Yes
119 | 14. Test & Validation | Data mapping Assigned | Solution Architecture | Enabling | Collaboration | 114,115,116,118 | Approval Gate | Waiting | All lanes | Every workload | 36 | 6 | 9.9 | 3.4 | 0.62 | 0.1429 | 5.25 | 721.5 | 726.75 | 721.5 | 726.75 | 0 | Yes
120 | 15. Resilience & DR | Cost model Confirmed | Procurement / Legal | Governance Function (not a TT team) | Handoff (TT anti-pattern) | 119 | Value-Add | - | All lanes | Every workload | 25 | 4 | 7.3 | 1.8 | 0.9 | 0.1379 | 3.625 | 726.75 | 730.38 | 726.75 | 730.38 | 0 | Yes
121 | 15. Resilience & DR | Network path Published | Integration Platforms | Complicated-Subsystem | X-as-a-Service | 120 | Business Non-Value-Add (Type 1 Muda) | Waiting | All lanes | Every workload | 55 | 7 | 15.8 | 4 | 0.72 | 0.1129 | 7.75 | 730.38 | 738.12 | 730.38 | 738.12 | 0 | Yes
122 | 15. Resilience & DR | Risk assessment Published | Platform Team | Platform | X-as-a-Service | 121 | Business Non-Value-Add (Type 1 Muda) | Extra-Processing | All lanes | Every workload | 48 | 6 | 13.8 | 3.5 | 0.85 | 0.1111 | 6.75 | 738.12 | 744.88 | 738.12 | 744.88 | 0 | Yes
123 | 15. Resilience & DR | Deployment artefact Reviewed | Solution Architecture | Enabling | Collaboration | 120 | Rework Loop | Defects | All lanes | Every workload | 40 | 5 | 11.7 | 2.9 | 0.58 | 0.1111 | 5.625 | 730.38 | 736 | 739.25 | 744.88 | 8.88
124 | 16. Security Evidence & Signoff | Pattern selection Completed | Integration Platforms | Complicated-Subsystem | X-as-a-Service | 122,123 | Value-Add | - | All lanes | Every workload | 62 | 8 | 14.9 | 4 | 0.94 | 0.1143 | 8.75 | 744.88 | 753.62 | 744.88 | 753.62 | 0 | Yes
125 | 16. Security Evidence & Signoff | Access model Reviewed | Delivery Leadership | Stream-Aligned | Collaboration | 124 | Approval Gate | Waiting | All lanes | Every workload | 60 | 7 | 14.2 | 3.8 | 0.61 | 0.1045 | 8.375 | 753.62 | 762 | 753.62 | 762 | 0 | Yes
126 | 16. Security Evidence & Signoff | Design package Validated | Stream-Aligned Team | Stream-Aligned | Collaboration | 125 | Approval Gate | Waiting | All lanes | Every workload | 63 | 8 | 15.1 | 4.1 | 0.57 | 0.1127 | 8.875 | 762 | 770.88 | 762 | 770.88 | 0 | Yes
127 | 16. Security Evidence & Signoff | Network path Approved | Cybersecurity | Complicated-Subsystem | X-as-a-Service | 126 | Value-Add | - | All lanes | Every workload | 39 | 5 | 9.4 | 2.5 | 0.87 | 0.1136 | 5.5 | 770.88 | 776.38 | 770.88 | 776.38 | 0 | Yes
128 | 17. Production Readiness & Change | Exception request Validated | Platform Engineering | Platform | Handoff (TT anti-pattern) | 127 | Handoff | Transportation | All lanes | Every workload | 25 | 3 | 6.6 | 1.6 | 0.6 | 0.1071 | 3.5 | 776.38 | 779.88 | 776.38 | 779.88 | 0 | Yes
129 | 17. Production Readiness & Change | Access model Documented | Solution Architecture | Enabling | Facilitating | 128 | Business Non-Value-Add (Type 1 Muda) | - | All lanes | Every workload | 31 | 3 | 8.3 | 1.9 | 0.74 | 0.0882 | 4.25 | 779.88 | 784.12 | 779.88 | 784.12 | 0 | Yes
130 | 17. Production Readiness & Change | Cost model Executed | Cloud Platform | Platform | X-as-a-Service | 128 | Value-Add | - | Conditional | Non-standard decisions | 31 | 3 | 8.4 | 2 | 0.9 | 0.0882 | 4.25 | 779.88 | 784.12 | 779.88 | 784.12 | 0 | Yes
131 | 17. Production Readiness & Change | Intake record Onboarded | Network Security | Complicated-Subsystem | Collaboration | 129,130 | Approval Gate | Waiting | All lanes | Every workload | 31 | 3 | 8.3 | 1.9 | 0.76 | 0.0882 | 4.25 | 784.12 | 788.38 | 784.12 | 788.38 | 0 | Yes
132 | 17. Production Readiness & Change | Exception request Configured | Cybersecurity | Complicated-Subsystem | X-as-a-Service | 131 | Value-Add | - | Conditional | GenAI use cases | 26 | 3 | 6.8 | 1.6 | 0.97 | 0.1034 | 3.625 | 788.38 | 792 | 788.38 | 792 | 0 | Yes
133 | 17. Production Readiness & Change | Risk assessment Reviewed | Cloud Platform | Platform | Collaboration | 131,132 | Approval Gate | Waiting | All lanes | Every workload | 29 | 3 | 7.8 | 1.8 | 0.61 | 0.0938 | 4 | 792 | 796 | 792 | 796 | 0 | Yes
134 | 17. Production Readiness & Change | Access model Drafted | AI Governance Board | Governance Function (not a TT team) | Handoff (TT anti-pattern) | 133 | Business Non-Value-Add (Type 1 Muda) | Waiting | All lanes | Every workload | 17 | 2 | 4.5 | 1 | 0.77 | 0.1053 | 2.375 | 796 | 798.38 | 796 | 798.38 | 0 | Yes
135 | 17. Production Readiness & Change | Runbook Provisioned | Finance / PMO | Governance Function (not a TT team) | Handoff (TT anti-pattern) | 134 | Approval Gate | Waiting | Conditional | Internet-facing only | 34 | 4 | 8.9 | 2.1 | 0.69 | 0.1053 | 4.75 | 798.38 | 803.12 | 798.38 | 803.12 | 0 | Yes
136 | 18. Go-Live & Hypercare | Access model Confirmed | Enabling Architecture | Enabling | Facilitating | 135 | Value-Add | - | All lanes | Every workload | 18 | 3 | 5.3 | 1.5 | 0.89 | 0.1429 | 2.625 | 803.12 | 805.75 | 803.12 | 805.75 | 0 | Yes
137 | 18. Go-Live & Hypercare | Test plan Documented | Resource Management | Governance Function (not a TT team) | Handoff (TT anti-pattern) | 136 | Approval Gate | Waiting | All lanes | Every workload | 20 | 3 | 6 | 1.7 | 0.79 | 0.1304 | 2.875 | 805.75 | 808.62 | 805.75 | 808.62 | 0 | Yes
138 | 18. Go-Live & Hypercare | Runbook Validated | Finance / PMO | Governance Function (not a TT team) | Handoff (TT anti-pattern) | 137 | Value-Add | - | All lanes | Every workload | 12 | 2 | 3.7 | 1.1 | 0.81 | 0.1429 | 1.75 | 808.62 | 810.38 | 808.62 | 810.38 | 0 | Yes
139 | 18. Go-Live & Hypercare | Deployment artefact Confirmed | AI Governance | Governance Function (not a TT team) | Handoff (TT anti-pattern) | 137,138 | Approval Gate | Waiting | All lanes | Every workload | 15 | 2 | 4.4 | 1.3 | 0.69 | 0.1176 | 2.125 | 810.38 | 812.5 | 810.38 | 812.5 | 0 | Yes
140 | 18. Go-Live & Hypercare | Pattern selection Submitted | Procurement / Legal | Governance Function (not a TT team) | Handoff (TT anti-pattern) | 139 | Value-Add | - | Standard + Custom | Buy or SaaS only | 17 | 2 | 5 | 1.5 | 0.96 | 0.1053 | 2.375 | 812.5 | 814.88 | 812.5 | 814.88 | 0 | Yes
141 | 18. Go-Live & Hypercare | Pattern selection Submitted | Cloud FinOps | Platform | X-as-a-Service | 140 | Value-Add | - | Conditional | Azure workloads | 16 | 2 | 4.7 | 1.4 | 0.8 | 0.1111 | 2.25 | 814.88 | 817.12 | 814.88 | 817.12 | 0 | Yes
142 | 18. Go-Live & Hypercare | Service record Reviewed | Procurement | Governance Function (not a TT team) | Handoff (TT anti-pattern) | 139 | Handoff | Transportation | All lanes | Every workload | 32 | 4 | 9.4 | 2.7 | 0.85 | 0.1111 | 4.5 | 812.5 | 817 | 812.62 | 817.12 | 0.12
143 | 19. Post Go-Live & Decommission | Design package Completed | Resilience Architecture | Complicated-Subsystem | X-as-a-Service | 141,142 | Business Non-Value-Add (Type 1 Muda) | Inventory | All lanes | Every workload | 72 | 7 | 25.9 | 4.7 | 0.7 | 0.0886 | 9.875 | 817.12 | 827 | 817.12 | 827 | 0 | Yes
144 | 19. Post Go-Live & Decommission | Cost model Onboarded | CMDB / Asset Mgmt | Platform | X-as-a-Service | 143 | Value-Add | - | Conditional | Regulated / personal data | 53 | 5 | 19 | 3.4 | 0.92 | 0.0862 | 7.25 | 827 | 834.25 | 827 | 834.25 | 0 | Yes
145 | 19. Post Go-Live & Decommission | Intake record Published | Data Privacy | Complicated-Subsystem | X-as-a-Service | 144 | Value-Add | - | All lanes | Every workload | 54 | 6 | 19.4 | 3.5 | 0.97 | 0.1 | 7.5 | 834.25 | 841.75 | 834.25 | 841.75 | 0 | Yes
146 | 19. Post Go-Live & Decommission | Cost model Drafted | Cloud Ops / SRE | Platform | X-as-a-Service | 145 | Value-Add | - | Conditional | Azure workloads | 41 | 4 | 14.7 | 2.6 | 0.88 | 0.0889 | 5.625 | 841.75 | 847.38 | 841.75 | 847.38 | 0 | Yes

## Edges
Successor ID | Predecessor ID | Successor Task | Predecessor Task | Predecessor Earliest Finish | Successor Earliest Start | Zero-Slack Link
2 | 1 | Service record Assigned | Deployment artefact Approved | 9.38 | 9.38 | BINDING
3 | 1 | Access model Confirmed | Deployment artefact Approved | 9.38 | 9.38 | BINDING
4 | 1 | Data mapping Completed | Deployment artefact Approved | 9.38 | 9.38 | BINDING
5 | 4 | Design package Published | Data mapping Completed | 21.25 | 21.25 | BINDING
6 | 2 | Test plan Assigned | Service record Assigned | 19.75 | 29.25
6 | 3 | Test plan Assigned | Access model Confirmed | 15.25 | 29.25
6 | 5 | Test plan Assigned | Design package Published | 29.25 | 29.25 | BINDING
7 | 6 | Network path Provisioned | Test plan Assigned | 35.88 | 35.88 | BINDING
8 | 7 | Design package Published | Network path Provisioned | 44.12 | 44.12 | BINDING
9 | 8 | Pattern selection Published | Design package Published | 49 | 49 | BINDING
10 | 9 | Test plan Drafted | Pattern selection Published | 59.5 | 59.5 | BINDING
11 | 10 | Control evidence Executed | Test plan Drafted | 68.38 | 68.38 | BINDING
12 | 11 | Readiness check Reviewed | Control evidence Executed | 76.88 | 76.88 | BINDING
13 | 11 | Test plan Signed off | Control evidence Executed | 76.88 | 89.25
13 | 12 | Test plan Signed off | Readiness check Reviewed | 89.25 | 89.25 | BINDING
14 | 13 | Service record Submitted | Test plan Signed off | 100.88 | 100.88 | BINDING
15 | 14 | Data mapping Signed off | Service record Submitted | 106.62 | 106.62 | BINDING
16 | 15 | Design package Documented | Data mapping Signed off | 131.25 | 131.25 | BINDING
17 | 16 | Readiness check Published | Design package Documented | 145.12 | 145.12 | BINDING
18 | 17 | Service record Signed off | Readiness check Published | 174.38 | 174.38 | BINDING
19 | 15 | Intake record Approved | Data mapping Signed off | 131.25 | 131.25 | BINDING
20 | 18 | Cost model Confirmed | Service record Signed off | 195.12 | 195.12 | BINDING
21 | 15 | Network path Signed off | Data mapping Signed off | 131.25 | 131.25 | BINDING
22 | 20 | Pattern selection Drafted | Cost model Confirmed | 210.5 | 210.5 | BINDING
22 | 19 | Pattern selection Drafted | Intake record Approved | 146.12 | 210.5
22 | 21 | Pattern selection Drafted | Network path Signed off | 153.25 | 210.5
23 | 22 | Data mapping Configured | Pattern selection Drafted | 225.88 | 225.88 | BINDING
24 | 22 | Cost model Documented | Pattern selection Drafted | 225.88 | 239.75
24 | 23 | Cost model Documented | Data mapping Configured | 239.75 | 239.75 | BINDING
25 | 24 | Pattern selection Submitted | Cost model Documented | 243.62 | 243.62 | BINDING
26 | 25 | Pattern selection Configured | Pattern selection Submitted | 247.62 | 247.62 | BINDING
27 | 26 | Control evidence Configured | Pattern selection Configured | 251.62 | 251.62 | BINDING
28 | 27 | Risk assessment Published | Control evidence Configured | 256.12 | 256.12 | BINDING
29 | 27 | Test plan Onboarded | Control evidence Configured | 256.12 | 256.12 | BINDING
30 | 28 | Test plan Executed | Risk assessment Published | 260.5 | 260.5 | BINDING
31 | 27 | Control evidence Drafted | Control evidence Configured | 256.12 | 256.12 | BINDING
32 | 30 | Control evidence Confirmed | Test plan Executed | 264.5 | 264.5 | BINDING
32 | 29 | Control evidence Confirmed | Test plan Onboarded | 262.5 | 264.5
32 | 31 | Control evidence Confirmed | Control evidence Drafted | 262.25 | 264.5
33 | 32 | Pattern selection Provisioned | Control evidence Confirmed | 267.62 | 267.62 | BINDING
34 | 33 | Design package Documented | Pattern selection Provisioned | 273.25 | 273.25 | BINDING
35 | 34 | Readiness check Provisioned | Design package Documented | 280 | 280 | BINDING
36 | 35 | Network path Onboarded | Readiness check Provisioned | 286.88 | 286.88 | BINDING
37 | 36 | Network path Completed | Network path Onboarded | 293.12 | 293.12 | BINDING
38 | 37 | Data mapping Assigned | Network path Completed | 299.62 | 299.62 | BINDING
39 | 37 | Cost model Validated | Network path Completed | 299.62 | 299.62 | BINDING
40 | 39 | Intake record Onboarded | Cost model Validated | 307.25 | 307.25 | BINDING
41 | 38 | Network path Submitted | Data mapping Assigned | 306.75 | 306.75 | BINDING
42 | 37 | Cost model Completed | Network path Completed | 299.62 | 299.62 | BINDING
43 | 40 | Intake record Confirmed | Intake record Onboarded | 310.5 | 310.5 | BINDING
43 | 41 | Intake record Confirmed | Network path Submitted | 309.75 | 310.5
43 | 42 | Intake record Confirmed | Cost model Completed | 303 | 310.5
44 | 43 | Access model Executed | Intake record Confirmed | 314 | 314 | BINDING
45 | 44 | Service record Completed | Access model Executed | 320.62 | 320.62 | BINDING
46 | 45 | Service record Onboarded | Service record Completed | 327.75 | 327.75 | BINDING
47 | 46 | Pattern selection Approved | Service record Onboarded | 335 | 335 | BINDING
48 | 44 | Network path Executed | Access model Executed | 320.62 | 320.62 | BINDING
49 | 47 | Design package Configured | Pattern selection Approved | 338.38 | 338.38 | BINDING
50 | 44 | Access model Drafted | Access model Executed | 320.62 | 320.62 | BINDING
51 | 50 | Access model Configured | Access model Drafted | 326.38 | 326.38 | BINDING
52 | 44 | Risk assessment Published | Access model Executed | 320.62 | 320.62 | BINDING
53 | 51 | Cost model Onboarded | Access model Configured | 330.88 | 330.88 | BINDING
54 | 48 | Network path Submitted | Network path Executed | 324.38 | 324.38 | BINDING
55 | 54 | Readiness check Documented | Network path Submitted | 329.88 | 342.25
55 | 49 | Readiness check Documented | Design package Configured | 342.25 | 342.25 | BINDING
55 | 53 | Readiness check Documented | Cost model Onboarded | 334.88 | 342.25
55 | 52 | Readiness check Documented | Risk assessment Published | 327.88 | 342.25
56 | 55 | Cost model Assigned | Readiness check Documented | 349.38 | 349.38 | BINDING
57 | 55 | Data mapping Drafted | Readiness check Documented | 349.38 | 349.38 | BINDING
58 | 56 | Design package Onboarded | Cost model Assigned | 353.25 | 353.25 | BINDING
59 | 57 | Runbook Confirmed | Data mapping Drafted | 355.75 | 355.75 | BINDING
60 | 59 | Cost model Drafted | Runbook Confirmed | 362 | 362 | BINDING
60 | 58 | Cost model Drafted | Design package Onboarded | 357.12 | 362
61 | 60 | Design package Reviewed | Cost model Drafted | 368 | 368 | BINDING
62 | 61 | Network path Signed off | Design package Reviewed | 374.12 | 374.12 | BINDING
63 | 62 | Data mapping Onboarded | Network path Signed off | 384.62 | 384.62 | BINDING
64 | 63 | Access model Reviewed | Data mapping Onboarded | 396.75 | 396.75 | BINDING
65 | 64 | Design package Confirmed | Access model Reviewed | 404.75 | 404.75 | BINDING
66 | 65 | Network path Documented | Design package Confirmed | 414.5 | 414.5 | BINDING
67 | 66 | Readiness check Provisioned | Network path Documented | 432.75 | 432.75 | BINDING
68 | 66 | Network path Onboarded | Network path Documented | 432.75 | 432.75 | BINDING
69 | 66 | Data mapping Approved | Network path Documented | 432.75 | 457.88
69 | 67 | Data mapping Approved | Readiness check Provisioned | 457.88 | 457.88 | BINDING
69 | 68 | Data mapping Approved | Network path Onboarded | 446.25 | 457.88
70 | 69 | Access model Assigned | Data mapping Approved | 477.25 | 477.25 | BINDING
71 | 69 | Readiness check Provisioned | Data mapping Approved | 477.25 | 490.75
71 | 70 | Readiness check Provisioned | Access model Assigned | 490.75 | 490.75 | BINDING
72 | 71 | Intake record Submitted | Readiness check Provisioned | 500.25 | 500.25 | BINDING
73 | 72 | Cost model Published | Intake record Submitted | 510.75 | 510.75 | BINDING
74 | 73 | Pattern selection Completed | Cost model Published | 527 | 527 | BINDING
75 | 73 | Risk assessment Configured | Cost model Published | 527 | 538.25
75 | 74 | Risk assessment Configured | Pattern selection Completed | 538.25 | 538.25 | BINDING
76 | 75 | Exception request Provisioned | Risk assessment Configured | 543.88 | 543.88 | BINDING
77 | 75 | Network path Documented | Risk assessment Configured | 543.88 | 543.88 | BINDING
78 | 77 | Data mapping Executed | Network path Documented | 548.5 | 548.5 | BINDING
79 | 75 | Risk assessment Confirmed | Risk assessment Configured | 543.88 | 543.88 | BINDING
80 | 79 | Test plan Validated | Risk assessment Confirmed | 548.38 | 548.38 | BINDING
81 | 75 | Service record Submitted | Risk assessment Configured | 543.88 | 543.88 | BINDING
82 | 80 | Cost model Onboarded | Test plan Validated | 554.62 | 554.62 | BINDING
83 | 76 | Pattern selection Provisioned | Exception request Provisioned | 550.38 | 564.25
83 | 78 | Pattern selection Provisioned | Data mapping Executed | 557.62 | 564.25
83 | 82 | Pattern selection Provisioned | Cost model Onboarded | 564.25 | 564.25 | BINDING
83 | 81 | Pattern selection Provisioned | Service record Submitted | 549.12 | 564.25
84 | 83 | Cost model Provisioned | Pattern selection Provisioned | 570.88 | 570.88 | BINDING
85 | 84 | Network path Configured | Cost model Provisioned | 576.88 | 576.88 | BINDING
86 | 84 | Risk assessment Submitted | Cost model Provisioned | 576.88 | 576.88 | BINDING
87 | 84 | Risk assessment Confirmed | Cost model Provisioned | 576.88 | 576.88 | BINDING
88 | 84 | Access model Approved | Cost model Provisioned | 576.88 | 576.88 | BINDING
89 | 85 | Access model Signed off | Network path Configured | 582.88 | 582.88 | BINDING
90 | 89 | Network path Published | Access model Signed off | 589.62 | 589.62 | BINDING
91 | 90 | Service record Configured | Network path Published | 597.62 | 597.62 | BINDING
92 | 88 | Intake record Submitted | Access model Approved | 586.75 | 586.75 | BINDING
93 | 86 | Network path Confirmed | Risk assessment Submitted | 584.88 | 584.88 | BINDING
94 | 87 | Deployment artefact Drafted | Risk assessment Confirmed | 581.38 | 581.38 | BINDING
95 | 94 | Network path Published | Deployment artefact Drafted | 589.88 | 589.88 | BINDING
96 | 93 | Pattern selection Approved | Network path Confirmed | 593.62 | 604.12
96 | 91 | Pattern selection Approved | Service record Configured | 604.12 | 604.12 | BINDING
96 | 95 | Pattern selection Approved | Network path Published | 597.75 | 604.12
96 | 92 | Pattern selection Approved | Intake record Submitted | 593.75 | 604.12
97 | 96 | Test plan Submitted | Pattern selection Approved | 607.38 | 607.38 | BINDING
98 | 97 | Risk assessment Submitted | Test plan Submitted | 611 | 611 | BINDING
99 | 98 | Risk assessment Signed off | Risk assessment Submitted | 617.75 | 617.75 | BINDING
100 | 99 | Cost model Published | Risk assessment Signed off | 623.25 | 623.25 | BINDING
101 | 100 | Test plan Configured | Cost model Published | 628.12 | 628.12 | BINDING
102 | 101 | Intake record Signed off | Test plan Configured | 636.62 | 636.62 | BINDING
103 | 101 | Test plan Provisioned | Test plan Configured | 636.62 | 636.62 | BINDING
104 | 102 | Access model Validated | Intake record Signed off | 641.25 | 644.88
104 | 103 | Access model Validated | Test plan Provisioned | 644.88 | 644.88 | BINDING
105 | 104 | Risk assessment Reviewed | Access model Validated | 648.62 | 648.62 | BINDING
106 | 104 | Cost model Configured | Access model Validated | 648.62 | 648.62 | BINDING
107 | 106 | Access model Submitted | Cost model Configured | 653.12 | 653.12 | BINDING
108 | 105 | Design package Executed | Risk assessment Reviewed | 652.25 | 652.25 | BINDING
109 | 107 | Runbook Onboarded | Access model Submitted | 659 | 659 | BINDING
110 | 104 | Readiness check Onboarded | Access model Validated | 648.62 | 665.25
110 | 108 | Readiness check Onboarded | Design package Executed | 657.25 | 665.25
110 | 109 | Readiness check Onboarded | Runbook Onboarded | 665.25 | 665.25 | BINDING
111 | 110 | Runbook Executed | Readiness check Onboarded | 673.12 | 673.12 | BINDING
112 | 110 | Test plan Drafted | Readiness check Onboarded | 673.12 | 673.12 | BINDING
113 | 110 | Risk assessment Executed | Readiness check Onboarded | 673.12 | 679.38
113 | 111 | Risk assessment Executed | Runbook Executed | 678.75 | 679.38
113 | 112 | Risk assessment Executed | Test plan Drafted | 679.38 | 679.38 | BINDING
114 | 113 | Service record Signed off | Risk assessment Executed | 686.75 | 686.75 | BINDING
115 | 114 | Risk assessment Executed | Service record Signed off | 698.38 | 698.38 | BINDING
116 | 114 | Deployment artefact Completed | Service record Signed off | 698.38 | 698.38 | BINDING
117 | 114 | Pattern selection Onboarded | Service record Signed off | 698.38 | 698.38 | BINDING
118 | 117 | Network path Configured | Pattern selection Onboarded | 711.75 | 711.75 | BINDING
119 | 114 | Data mapping Assigned | Service record Signed off | 698.38 | 721.5
119 | 115 | Data mapping Assigned | Risk assessment Executed | 706.88 | 721.5
119 | 116 | Data mapping Assigned | Deployment artefact Completed | 708.25 | 721.5
119 | 118 | Data mapping Assigned | Network path Configured | 721.5 | 721.5 | BINDING
120 | 119 | Cost model Confirmed | Data mapping Assigned | 726.75 | 726.75 | BINDING
121 | 120 | Network path Published | Cost model Confirmed | 730.38 | 730.38 | BINDING
122 | 121 | Risk assessment Published | Network path Published | 738.12 | 738.12 | BINDING
123 | 120 | Deployment artefact Reviewed | Cost model Confirmed | 730.38 | 730.38 | BINDING
124 | 122 | Pattern selection Completed | Risk assessment Published | 744.88 | 744.88 | BINDING
124 | 123 | Pattern selection Completed | Deployment artefact Reviewed | 736 | 744.88
125 | 124 | Access model Reviewed | Pattern selection Completed | 753.62 | 753.62 | BINDING
126 | 125 | Design package Validated | Access model Reviewed | 762 | 762 | BINDING
127 | 126 | Network path Approved | Design package Validated | 770.88 | 770.88 | BINDING
128 | 127 | Exception request Validated | Network path Approved | 776.38 | 776.38 | BINDING
129 | 128 | Access model Documented | Exception request Validated | 779.88 | 779.88 | BINDING
130 | 128 | Cost model Executed | Exception request Validated | 779.88 | 779.88 | BINDING
131 | 129 | Intake record Onboarded | Access model Documented | 784.12 | 784.12 | BINDING
131 | 130 | Intake record Onboarded | Cost model Executed | 784.12 | 784.12 | BINDING
132 | 131 | Exception request Configured | Intake record Onboarded | 788.38 | 788.38 | BINDING
133 | 131 | Risk assessment Reviewed | Intake record Onboarded | 788.38 | 792
133 | 132 | Risk assessment Reviewed | Exception request Configured | 792 | 792 | BINDING
134 | 133 | Access model Drafted | Risk assessment Reviewed | 796 | 796 | BINDING
135 | 134 | Runbook Provisioned | Access model Drafted | 798.38 | 798.38 | BINDING
136 | 135 | Access model Confirmed | Runbook Provisioned | 803.12 | 803.12 | BINDING
137 | 136 | Test plan Documented | Access model Confirmed | 805.75 | 805.75 | BINDING
138 | 137 | Runbook Validated | Test plan Documented | 808.62 | 808.62 | BINDING
139 | 137 | Deployment artefact Confirmed | Test plan Documented | 808.62 | 810.38
139 | 138 | Deployment artefact Confirmed | Runbook Validated | 810.38 | 810.38 | BINDING
140 | 139 | Pattern selection Submitted | Deployment artefact Confirmed | 812.5 | 812.5 | BINDING
141 | 140 | Pattern selection Submitted | Pattern selection Submitted | 814.88 | 814.88 | BINDING
142 | 139 | Service record Reviewed | Deployment artefact Confirmed | 812.5 | 812.5 | BINDING
143 | 141 | Design package Completed | Pattern selection Submitted | 817.12 | 817.12 | BINDING
143 | 142 | Design package Completed | Service record Reviewed | 817 | 817.12
144 | 143 | Cost model Onboarded | Design package Completed | 827 | 827 | BINDING
145 | 144 | Intake record Published | Cost model Onboarded | 834.25 | 834.25 | BINDING
146 | 145 | Cost model Drafted | Intake record Published | 841.75 | 841.75 | BINDING

## Toggles
Toggle ID | Group | Label | Type | Options | Default | Implies | Help
workType | Work Type | What kind of work is this | choice | Greenfield build;Lift and shift;COTS or SaaS adoption;Capacity extension;In-place upgrade;Decommission | Greenfield build |  | Sets the baseline task list. Exactly one.
discovery | Scope | Upfront discovery phase | boolean |  | No |  | Kickoff, requirements gathering, peer review, stakeholder validation, ARB.
rfi | Sourcing | Request for Information | boolean |  | No | discovery
rfp | Sourcing | Request for Proposal | boolean |  | No | discovery
poc | Sourcing | Proof of concept or pilot | boolean |  | No | discovery
newVendor | Sourcing | New vendor to the organization | boolean |  | No |  | Triggers TPRM and vendor onboarding.
hardware | Sourcing | Hardware purchase | boolean |  | No
newLicense | Sourcing | New or expanded licensing | boolean |  | No
genAI | Technical | AI or GenAI workload | boolean |  | No |  | Adds the AI governance chain.
pavedRoad | Technical | Standard pattern from the catalog | boolean |  | No |  | Pre-approved modules, so several reviews stop applying.
newService | Technical | Cloud service type not previously approved | boolean |  | No
dataMigration | Technical | Data migration required | boolean |  | No
tier | Risk | Service tier | choice | Tier 0;Tier 1;Tier 2;Tier 3;Tier 4 | Tier 3
dataClass | Risk | Data classification | choice | Public;Internal;Confidential;Regulated | Confidential
internetFacing | Risk | Internet-facing | boolean |  | No
drRequired | Risk | DR required | boolean |  | Yes

## Profiles
Profile ID | Label | Description | workType | discovery | rfi | rfp | poc | newVendor | hardware | newLicense | genAI | pavedRoad | newService | dataMigration | tier | dataClass | internetFacing | drRequired
standard-paved | Standard paved-road app | Catalog pattern, internal data, no sourcing. | Greenfield build | No | No | No | No | No | No |  |  | Yes | No | No
lift-shift | Lift and shift, existing vendor | Move an existing app to cloud with no redesign. | Lift and shift | No | No | No | No | No | No |  |  | No |  | Yes
cots-rfp | COTS or SaaS purchase with RFP | Evaluate and buy a product, then onboard the vendor. | COTS or SaaS adoption | Yes | Yes | Yes | Yes | Yes |  | Yes |  | No
capacity-add | Regional capacity add | One more server in an existing footprint. No new app. | Capacity extension | No | No | No | No | No | Yes |  |  | Yes | No | No
upgrade | In-place upgrade | OS, platform or software version uplift on what is already there. | In-place upgrade | No | No | No | No | No | No |  |  | No | No | No
greenfield-pioneer | Greenfield pioneering | New build using services we have not run before, with sourcing. | Greenfield build | Yes | Yes | Yes | Yes | Yes | Yes |  |  | No | Yes | No

## Scenario Matrix
Task ID | Task | Baseline | workType=Greenfield build | workType=Lift and shift | workType=COTS or SaaS adoption | workType=Capacity extension | workType=In-place upgrade | workType=Decommission | discovery | rfi | rfp | poc | newVendor | hardware | newLicense | genAI | pavedRoad | newService | dataMigration | tier=Tier 0¦Tier 1 | dataClass=Regulated | internetFacing | drRequired
1 | Deployment artefact Approved | Yes
2 | Service record Assigned | Yes
3 | Access model Confirmed | Yes
4 | Data mapping Completed | Yes
5 | Design package Published | Yes
6 | Test plan Assigned | Yes
7 | Network path Provisioned | Yes
8 | Design package Published | Yes
9 | Pattern selection Published | Yes
10 | Test plan Drafted | Yes
11 | Control evidence Executed | Yes
12 | Readiness check Reviewed | Yes
13 | Test plan Signed off | No | [13 empty] | R
14 | Service record Submitted | Yes
15 | Data mapping Signed off | No | [6 empty] | R | R
16 | Design package Documented | No | [6 empty] | R |  | R
17 | Readiness check Published | No | [6 empty] | R |  |  | R
18 | Service record Signed off | No | [6 empty] | R | R
19 | Intake record Approved | No | [6 empty] | R |  | R
20 | Cost model Confirmed | No | [6 empty] | R |  |  | R
21 | Network path Signed off | No | [6 empty] | R | R
22 | Pattern selection Drafted | No | [6 empty] | R |  | R
23 | Data mapping Configured | No | [6 empty] | R |  |  | R
24 | Cost model Documented | Yes |  | N |  | N | N | N
25 | Pattern selection Submitted | Yes |  | N |  | N | N | N
26 | Pattern selection Configured | Yes |  | N |  | N | N | N
27 | Control evidence Configured | Yes |  | N |  | N | N | N
28 | Risk assessment Published | Yes |  | N |  | N | N | N
29 | Test plan Onboarded | Yes |  | N |  | N | N | N
30 | Test plan Executed | Yes |  | N |  | N | N | N
31 | Control evidence Drafted | Yes |  | N |  | N | N | N
32 | Control evidence Confirmed | Yes |  |  |  | N | N | N
33 | Pattern selection Provisioned | Yes |  |  |  | N | N | N
34 | Design package Documented | Yes |  |  |  | N | N | N
35 | Readiness check Provisioned | Yes |  |  |  | N | N | N
36 | Network path Onboarded | Yes |  |  |  | N | N | N
37 | Network path Completed | Yes |  |  |  | N | N | N
38 | Data mapping Assigned | Yes |  |  |  | N | N | N
39 | Cost model Validated | Yes |  |  |  | N | N | N
40 | Intake record Onboarded | Yes |  |  |  | N | N | N
41 | Network path Submitted | Yes |  |  |  | N | N | N
42 | Cost model Completed | Yes |  |  |  | N | N | N
43 | Intake record Confirmed | Yes |  |  |  | N | N | N
44 | Access model Executed | Yes |  |  |  | N | N | N | [9 empty] | 1.8
45 | Service record Completed | Yes |  |  |  | N | N | N
46 | Service record Onboarded | Yes |  |  |  | N | N | N
47 | Pattern selection Approved | Yes |  |  |  | N | N | N
48 | Network path Executed | Yes |  |  |  | N | N | N | [9 empty] | 1.8
49 | Design package Configured | Yes |  |  |  | N | N | N
50 | Access model Drafted | Yes |  |  |  | N | N | N
51 | Access model Configured | Yes |  |  |  | N | N | N
52 | Risk assessment Published | No | [13 empty] | R
53 | Cost model Onboarded | Yes |  |  |  | N | N | N
54 | Network path Submitted | Yes |  |  |  | N | N | N
55 | Readiness check Documented | Yes |  |  |  | N | N | N | [8 empty] | N
56 | Cost model Assigned | Yes |  |  |  | N | N | N | [9 empty] | 1.8
57 | Data mapping Drafted | Yes |  |  |  | N | N | N
58 | Design package Onboarded | Yes |  |  |  | N | N | N
59 | Runbook Confirmed | Yes |  |  |  | N | N | N
60 | Cost model Drafted | Yes |  | N |  | N | N | N | [8 empty] | N | 2.5
61 | Design package Reviewed | Yes |  | N |  | N | N | N | [8 empty] | N | 2.5
62 | Network path Signed off | Yes |  | N |  | N | N | N | [8 empty] | N | 2.5
63 | Data mapping Onboarded | Yes |  | N |  | N | N | N | [8 empty] | N | 2.5
64 | Access model Reviewed | Yes |  | N |  | N | N | N | [8 empty] | N | 2.5
65 | Design package Confirmed | No | [13 empty] | R
66 | Network path Documented | No | [10 empty] | R | R | R
67 | Readiness check Provisioned | No | [10 empty] | R | R | R
68 | Network path Onboarded | No | [10 empty] | R | R | R
69 | Data mapping Approved | No | [10 empty] | R | R | R
70 | Access model Assigned | No | [10 empty] | R | R | R
71 | Readiness check Provisioned | Yes |  |  |  | N | N | N | [11 empty] | 1.5
72 | Intake record Submitted | Yes |  |  |  | N | N | N | [11 empty] | 1.5
73 | Cost model Published | Yes |  |  |  | N | N | N | [11 empty] | 1.5
74 | Pattern selection Completed | Yes |  |  |  | N | N | N | [12 empty] | 1.4
75 | Risk assessment Configured | Yes |  |  |  | N | N | N
76 | Exception request Provisioned | Yes |  |  |  | N | N | N
77 | Network path Documented | Yes |  |  |  | N | N | N
78 | Data mapping Executed | Yes |  |  |  | N | N | N
79 | Risk assessment Confirmed | Yes |  |  |  | N | N | N
80 | Test plan Validated | Yes |  |  |  | N | N | N
81 | Service record Submitted | Yes |  |  |  | N | N | N
82 | Cost model Onboarded | Yes |  |  |  | N | N | N
83 | Pattern selection Provisioned | Yes |  |  |  | N | N | N | [8 empty] | N
84 | Cost model Provisioned | Yes |  |  |  | N | N | N
85 | Network path Configured | Yes |  |  |  | N | N | N
86 | Risk assessment Submitted | Yes |  |  |  | N | N | N
87 | Risk assessment Confirmed | Yes |  |  |  | N | N | N
88 | Access model Approved | Yes |  |  |  | N | N | N
89 | Access model Signed off | Yes |  |  |  | N | N | N
90 | Network path Published | Yes |  |  |  | N | N | N
91 | Service record Configured | Yes |  |  |  | N | N | N
92 | Intake record Submitted | Yes |  |  |  | N | N | N
93 | Network path Confirmed | Yes |  |  |  | N | N | N
94 | Deployment artefact Drafted | Yes |  |  |  | N | N | N
95 | Network path Published | Yes |  |  |  | N | N | N
96 | Pattern selection Approved | No |  |  |  | N | N | N | [13 empty] | R
97 | Test plan Submitted | Yes |  |  |  | N | N | N
98 | Risk assessment Submitted | No |  |  |  | N | N | N | [13 empty] | R
99 | Risk assessment Signed off | Yes |  |  |  | N | N | N
100 | Cost model Published | No |  |  |  | N | N | N | [13 empty] | R
101 | Test plan Configured | No | [16 empty] | R
102 | Intake record Signed off | No | [16 empty] | R
103 | Test plan Provisioned | No | [16 empty] | R
104 | Access model Validated | Yes |  |  |  | N | N | N
105 | Risk assessment Reviewed | Yes |  |  |  | N | N | N
106 | Cost model Configured | Yes |  |  |  | N | N | N
107 | Access model Submitted | Yes |  |  |  | N | N | N
108 | Design package Executed | Yes |  |  |  | N | N | N
109 | Runbook Onboarded | Yes |  |  |  | N | N | N
110 | Readiness check Onboarded | Yes |  |  |  | N | N | N
111 | Runbook Executed | Yes |  |  |  | N | N | N
112 | Test plan Drafted | Yes |  |  |  | N | N | N
113 | Risk assessment Executed | Yes |  |  |  | N | N | N
114 | Service record Signed off | Yes |  |  |  | N | N | N
115 | Risk assessment Executed | Yes |  |  |  | N | N | N
116 | Deployment artefact Completed | Yes |  |  |  | N | N | N
117 | Pattern selection Onboarded | No | [13 empty] | R
118 | Network path Configured | Yes |  |  |  | N | N | N
119 | Data mapping Assigned | Yes |  |  |  | N | N | N
120 | Cost model Confirmed | No | [20 empty] | R
121 | Network path Published | No | [20 empty] | R
122 | Risk assessment Published | No | [20 empty] | R
123 | Deployment artefact Reviewed | No | [20 empty] | R
124 | Pattern selection Completed | Yes |  |  |  | N | N | N
125 | Access model Reviewed | Yes |  |  |  | N | N | N | [11 empty] | 1.5
126 | Design package Validated | Yes |  |  |  | N | N | N | [11 empty] | 1.5
127 | Network path Approved | Yes |  |  |  | N | N | N
128 | Exception request Validated | Yes
129 | Access model Documented | Yes
130 | Cost model Executed | No | [13 empty] | R
131 | Intake record Onboarded | Yes | [17 empty] | 1.5
132 | Exception request Configured | Yes
133 | Risk assessment Reviewed | Yes | [17 empty] | 1.5
134 | Access model Drafted | Yes
135 | Runbook Provisioned | Yes | [17 empty] | 1.5
136 | Access model Confirmed | Yes
137 | Test plan Documented | Yes
138 | Runbook Validated | Yes
139 | Deployment artefact Confirmed | Yes
140 | Pattern selection Submitted | Yes
141 | Pattern selection Submitted | Yes
142 | Service record Reviewed | Yes
143 | Design package Completed | Yes
144 | Cost model Onboarded | Yes
145 | Intake record Published | Yes
146 | Cost model Drafted | Yes

## Assumptions
Step Type (Lean) | Lead Time Reduction Factor | Cycle Time Reduction Factor
Approval Gate | 0.8 | 0.5
Handoff | 0.85 | 0.5
Rework Loop | 0.85 | 0.7
Business Non-Value-Add (Type 1 Muda) | 0.7 | 0.4
Waste (Type 2 Muda) | 1 | 1
Value-Add | 0.6 | 0.3
Milestone | 0.5 | 0

## Summary by Phase
Phase | Steps | Approval Gates | Handoffs | Rework Loops | Current Lead (hrs) | Current Cycle (hrs) | Optimized Lead (hrs) | Optimized Cycle (hrs) | Lead Time Reduction (hrs) | Flow Efficiency %
1. Concept & Demand | 14 | 5 | 1 | 2 | 926 | 57 | 189.5 | 28.1 | 765.4 | 5.8
2. Discovery & Product Selection | 9 | 2 | 0 | 0 | 1152 | 208 | 357.6 | 124.8 | 877.6 | 15.3
3. Placement & Pattern Selection | 8 | 4 | 0 | 0 | 272 | 26 | 78.4 | 16.6 | 203 | 8.7
4. Requirements & Classification | 12 | 2 | 0 | 0 | 448 | 56 | 150 | 36.4 | 317.6 | 11.1
5. Architecture & Design | 16 | 1 | 0 | 1 | 608 | 84 | 198 | 51.2 | 442.8 | 12.1
6. Architecture Governance | 6 | 5 | 0 | 0 | 400 | 20 | 82 | 10 | 328 | 4.8
7. Procurement & Vendor | 5 | 1 | 0 | 0 | 680 | 38 | 162 | 19 | 537 | 5.3
8. Security & Privacy Approvals | 4 | 3 | 0 | 0 | 360 | 20 | 74 | 10 | 296 | 5.3
9. Provisioning (Pipeline / IaC) | 9 | 1 | 0 | 0 | 412 | 53 | 135.6 | 34.5 | 294.9 | 11.4
10. Platform & Middleware Integration | 12 | 0 | 0 | 0 | 648 | 54 | 222 | 34.2 | 445.8 | 7.7
11. Network & Connectivity | 5 | 1 | 1 | 0 | 180 | 12 | 40.4 | 5.8 | 145.8 | 6.2
12. Data | 3 | 0 | 0 | 0 | 144 | 27 | 54 | 18.3 | 98.7 | 15.8
13. Observability & Ops Readiness | 6 | 1 | 0 | 1 | 208 | 24 | 59.6 | 13.8 | 158.6 | 10.3
14. Test & Validation | 10 | 3 | 0 | 1 | 588 | 96 | 161.4 | 55.2 | 467.4 | 14
15. Resilience & DR | 4 | 0 | 0 | 1 | 168 | 22 | 48.6 | 12.2 | 129.2 | 11.6
16. Security Evidence & Signoff | 4 | 2 | 0 | 0 | 224 | 28 | 53.6 | 14.4 | 184 | 11.1
17. Production Readiness & Change | 8 | 3 | 1 | 0 | 224 | 24 | 59.6 | 13.9 | 174.5 | 9.7
18. Go-Live & Hypercare | 7 | 2 | 1 | 0 | 130 | 18 | 38.5 | 11.2 | 98.3 | 12.2
19. Post Go-Live & Decommission | 4 | 0 | 0 | 0 | 220 | 22 | 79 | 14.2 | 148.8 | 9.1